## Plan Summary
Student | Brian Alexander | Assign. | 7 |  | Date | 2019-06-11
Instructor | Andrew Clifton |  |  |  | Course | CS 133
Final |  | Estimate |  | Actual
LOC/Hour |  | 0.65 |  | 0.35436
Program Size (LOC) |  | Estimate |  | Actual
Created |  | 160 |  | 191
|  | (estimated) |  | (counted)
Δ Lines |  | 30 |  | 62
|  | (estimated) |  | (counted)
Final LOC |  | 130 |  | 191
(counted)
Time in Phase (min) |  | Estimate |  | Actual
Planning |  | 20 |  | 101
Design |  | 20 |  | 126
Code |  | 120 |  | 266
Compile |  | 10 |  | 12
Test |  | 10 |  | 22
Postmortem |  | 20 |  | 12
TOTAL |  | 200 |  | 539
Defects injected |  | Estimate |  | Actual
Planning |  | 5 |  | 4
Design |  | 10 |  | 7
Code |  | 10 |  | 12
Compile |  | 1 |  | 0
Test |  | 2 |  | 0
TOTAL |  | 28 |  | 23
Defects removed |  | Estimate |  | Actual
Planning |  | 0 |  | 0
Design |  | 5 |  | 2
Code |  | 10 |  | 16
Compile |  | 1 |  | 0
Test |  | 12 |  | 5
TOTAL development |  | 28 |  | 23
Post-development |  | 0 |  | 0

## Time log
Student | Brian Alexander |  |  |  |  | Date | 2019-06-11
Instructor | Andrew Clifton |  |  |  |  | Course | CS 133
Date | Phase | Start time | Int. mins. | End time | Total | Comments
2019-06-11 | Plan | 10:22 | 5 | 11:08 | 41 | Plan data structures |  | Totals per phase | Minutes
2019-06-11 | Plan | 15:04 | 13 | 16:17 | 60 | Work on logic |  | Plan | 101
2019-06-11 | Design | 21:35 | 36 | 23:57 | 106 | Refine structures & logic |  | Design | 126
2019-06-15 | Code | 20:21 | 17 | 21:31 | 53 | implement easy functions |  | Code | 266
2019-06-15 | Compile | 21:31 | 0 | 21:33 | 2 |  |  | Compile | 12
2019-06-15 | Test | 21:33 | 0 | 21:37 | 4 |  |  | Test | 22
2019-06-15 | Design | 21:37 | 0 | 21:57 | 20 | rework data structures
2019-06-15 | Code | 22:05 | 17 | 23:59 | 97 | implement new data structure
2019-06-16 | Compile | 0:00 | 0 | 0:04 | 4
2019-06-18 | Code | 13:41 | 0 | 14:26 | 45 | implement BFS
2019-06-18 | Compile | 14:26 | 0 | 14:29 | 3
2019-06-18 | Test | 14:29 | 0 | 14:45 | 16
2019-06-18 | Code | 22:41 | 0 | 23:52 | 71 | finalize BFS
2019-06-18 | Compile | 23:52 | 0 | 23:55 | 3
2019-06-18 | Test | 23:55 | 0 | 23:57 | 2
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Defect log
| Student | Brian Alexander | [5 empty] | Date | 2019-06-11
| Instructor | Andrew Clifton | [5 empty] | Course | CS 133
Types
# | Inject | Remove | Type | Fix time (min) | ΔL | Fix ref. | Description |  |  | Docs | Documentation
1 | Plan | Design | Data | 8 | 0 |  | Data structure isnt working |  |  | Syntax | Syntax, typo, punctuation
2 | Plan | Design | Logic | 11 | 0 |  | Logic for add node not working |  |  | Build | Compilation and linking
3 | Plan | Code | Data | 7 | 5 |  | queue |  |  | Variable | Naming, assignment, type
4 | Plan | Code | Logic | 5 | 6 |  | queue logic |  |  | Interface | Public members/methods, function sig.
5 | Design | Code | Data | 6 | 3 |  | adjust data structures |  |  | Checking | Checking assumptions
6 | Design | Code | Logic | 7 | 3 |  | walking through queue |  |  | Data | Data structures, values
7 | Design | Code | Data | 11 | 2 |  | storing distances |  |  | Logic | Loops, conditions, pointers, recursion
8 | Design | Code | Logic | 12 | 5 |  | counting edges |  |  | System | IO, timing, OS interaction
9 | Design | Code | Logic | 7 | 5 |  | adding edge logic |  |  | Env | Editor, version control, SSH
10 | Code | Test | Syntax | 2 | 1 |  | pointer
11 | Code | Test | Data | 15 | 3 |  |  |  |  | Injects by phase
12 | Code | Code | Syntax | 2 | 1 |  | pointer/dereference |  |  | Plan | 4
13 | Code | Code | Syntax | 1 | 1 |  | template type |  |  | Design | 7
14 | Code | Code | Variable | 3 | 1 |  | type |  |  | Code | 12
15 | Code | Code | Variable | 2 | 1 |  | type |  |  | Compile | 0
16 | Design | Code | Logic | 14 | 9 |  | reuse has_edge |  |  | Test | 0
17 | Design | Code | Logic | 18 | 6 |  | reuse bfs()
18 | Code | Test | Syntax | 3 | 2 |  | pointer |  |  | Removal by phase
19 | Code | Test | Syntax | 4 | 1 |  | using arrow operator |  |  | Plan | 0
20 | Code | Test | Logic | 8 | 3 |  |  |  |  | Design | 2
21 | Code | Code | Variable | 2 | 1 |  | name |  |  | Code | 16
22 | Code | Code | Syntax | 3 | 2 |  | typo |  |  | Compile | 0
23 | Code | Code | Syntax | 4 | 1 |  | punctuation |  |  | Test | 5
24
25 | [9 empty] | Defects by type
26 | [9 empty] | Docs | 0
27 | [9 empty] | Syntax | 7
28 | [9 empty] | Build | 0
29 | [9 empty] | Variable | 3
30 | [9 empty] | Interface | 0
31 | [9 empty] | Checking | 0
32 | [9 empty] | Data | 5
33 | [9 empty] | Logic | 8
34 | [9 empty] | System | 0
35 | [9 empty] | Env | 0
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100